## Sheet1
Defect # | Description | Detected Stage | Affected Tests | Type of Defect | Severity | Impact | Priority | Injected Stage | Action Taken
1 | Non-positive integer inputs for loan amount or loan years result in positive values instead of error | Testing | EPTC7, EPTC14, | Logical | Moderate | Incorrect calculations | medium | Design | Added validation to check if loan amount or loan years are ≤ 0 and return -1 for invalid inputs.
BVATC12,BVATC24
2 | Program crashes when user enters non-numeric characters for loan amount or loan years | Testing | EPTC15, EPTC16 | Logical | High | System crash | High | Design | Added an if statement to handle string characters
3 | Loan amounts over $500,000 with yearLoan < 11 return as invalid, though the condition is unclear. | Coding | CT1, CT2 | Conditional | Moderate | Incorrect rejection | Medium | Requirements | Will confirm with the client about the conditions and report
4 | Null inputs should return “Invalid input” message but instead returns 0 | Testing | EPTC6, EPTC13, BVATC11, BVATC23 |  | Low | Incorrect output | Low | Design | Added an if statement to handle null values
5 | There is no upper limit for loan amount so user could request for an unlimited amount of loan | Coding | - | Conditional | Low | Users could ask for loans the organization doesn’t have the resources for | Low | Desigm | Will confirm with the client about the conditions and report